## Gantt Chart
GANTT CHART
PROJECT TITLE |  | KEYSTONE |  |  |  | ORGANIZATION NAME |  | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  | DATE |  | 2022-02-04
GROUP LEADER |  | Joe Trotti | [6 empty] | Job Completed
GROUP MEMBERS |  | Damien Brandel, Tanner Festa, Evan Finke, Alexis Rivera, Humza Shah, Joe Terranova | [6 empty] | Job In Process
Job Incomplete
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION
[6 empty] | W1 1/31/2022 | W2 2/7/2022 |  |  | W3 2/14/2022 | W4 2/21/2021 | W5 2/28/2022 | W6 3/7/2022 | W7 3/14/2022 | W8 3/21/2022 | W9 3/28/2022 | W10 4/4/2022 | W11 4/11/2022 | W12 4/18/2022 | W13 4/25/2022 | W14 5/2/2022
1 | Project Conception and Initiation
1.1 | Setting up Github | Everyone | 2022-01-31 | 2022-02-04 | 4
1.2 | Setting up Webex Account | Everyone | 2022-01-31 | 2022-02-04 | 4
1.3 | Setting up Unreal Engine | Everyone | 2022-02-03 | 2022-02-03 | 0
1.4 | Assigning Group Leader | Everyone | 2022-02-03 | 2022-02-03 | 0
1.5 | Setting up Discord | Everyone | 2022-02-02 | 2022-02-02 | 0
2 | Design
2.1 | Setting up Start Menu | Tanner | 2022-02-03 | 2022-02-07 | 0
2.2 | Setting up Pause Menu | Tanner | 2022-02-03 | 2022-02-07 | 4
2.3 | Pause Menu Design | Tanner | 2022-03-17
| Save Items in Inventory | Tanner | 2022-04-14
2.4 | Start Menu Design | Tanner | 2022-03-17
2.3 | Map Layout Level 1 | Joe Trotti | 2022-02-04 | 2022-04-05 | 61
2.5 | Map Layout Level 2 | Joe Trotti | 2022-02-21
2.6 | Map Design Level 1 | Joe Trotti | 2022-02-04 | 2022-04-05
2.7 | Map Design Level 2 | Joe Trotti | 2022-03-20
2.8 | Design Health Bar/ Stamina Bar/ Magic Bar | Damien | 2022-02-04 | 2022-02-05 | 0
2.9 | Configure Ability Tree | Damien | 2022-03-10 | 2022-04-08
2.1 | Player Abilities | Damien | 2022-02-04 | 2022-02-24 | 20
2.11 | Player Inventory | Joe Terranova | 2022-02-04 | 2022-02-11 | 0
2.12 | Audio | Evan | 2/30/2022 |  | #VALUE!
2.13 | Rating |  |  |  | 0
3 | Parts and Assembly
3.1 | Player Animations | Evan | 2022-02-03 | 2022-04-13 | 70
3.2 | Enemy Movement | Alexis | 2022-02-04 | 2022-02-22 | 0
3.3 | Items for Inventory | Joe Terranova | 2022-02-14 |  | -43964
3.4 | Use Inventory While in a Chest | Joe Terranova | 2022-03-17
3.5 | Player Combat | Alexis | 2022-02-23 |  | -43973
3.6 | Enemy Shield Mechanic | Alexis | 2022-03-17
6.7 | Save States | Tanner | 2022-02-17 | 2022-03-21 | 34
3.8 | Boss Movement | Humza | 2022-01-04 | 2022-02-22 | 0
3.9 | Boss Attacks | Humza | 2022-02-23 | 2022-03-16 | 0
3.1 | Servarog Boss | Humza | 2022-04-11
| Placing Basic enemies in world | Evan | 2022-04-21
3.11 | Dragon Attacks and Movement | Humza | 2022-02-23 |  | 0

## Sheet1
Damien
Tanner
Evan
Alexis
Humza
Joe Terranova
Joe Trotti
Everyone